## Sheet1
SCRUM NOTES
| Questions | Week 10 | Week 11 | Week 13 | Week 14 | Week 15 | Week 16 | Spring Week 1
Scrum Master | [7 empty] | Glenn
Glenn | What did you do | Quick Unity Recap | Found sample reference graphics for the game |  |  |  |  | Submitted Program and report | Submitted zip version of the program
|  | Created a tentative project timeline | C for Unity Recap | [5 empty] | Scaling issue fixed
Reviewed communication between machines(Networks)
| What will you do | Find sample graphics for the game | Graphcs Review |  |  |  |  | Fix the screen scaling issue | Fix game flow
| Issues experienced | N/A | N/A |  |  |  |  | Game Logic wasn't fully functional | Game flow completely ruined
The screen wasn't scaling properly
Ethan | What did you do | Defned scope of the project | C for Unity Recap |  |  |  |  | Submitted Program and report | Scaling issue fixed
|  | Created a tentative project timeline | Created a sample reference algorithm for the game
Reviewes basic functionality of the game
| What will you do | C for Unity Recap | Graphics review |  |  |  |  | Fix the screen scaling issue | Fix game logic
|  | Create a sample reference algorithm for the game | [6 empty] | Submit full game .zip file on github
| Issues experienced | N/A | N/A |  |  |  |  | Game Logic wasn't fully functional | .zip file is too large to upload on github
The screen wasn't scaling properly